## Project Management Dashboard
PROJECT MANAGEMENT DASHBOARD
PROJECT NAME | [Name]
REPORT DATE | [Date]
PROJECT STATUS | On track
COMPLETED | 27%
TASKS | ASSIGNED TO | PRIORITY | STATUS
Set Kick-Off Meeting | Alex B. |  | COMPLETE
Agree on Objectives | Frank C. | ★ | COMPLETE
Detailed Requests | Jacob S. |  | COMPLETE
Hardware Requests | Jacob S. | ★ | OVERDUE
Final Resource Plan | Jacob S. |  | IN PROGRESS
Staffing | Alex B. | ★ | IN PROGRESS
Technical Requests | Frank C. |  | NOT STARTED
Testing | Kennedy K. | ★ | NOT STARTED
Dev. Complete | Jacob S. | ★ | NOT STARTED
Hardware Configuration | Alex B. |  | NOT STARTED
System Testing | Kennedy K. | ★ | NOT STARTED
Launch

## Notes
Task Table
Tasks | Assigned To | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2022-09-02 | 2022-09-03 | 1 | COMPLETE
Agree on objectives | Frank C. | 2022-09-03 | 2022-09-07 | 4 | COMPLETE
Detailed Reqs. | Jacob S. | 2022-09-07 | 2022-09-12 | 5 | COMPLETE
Hardward Reqs. | Jacob S. | 2022-09-09 | 2022-09-11 | 2 | OVERDUE
Final Resource Plan | Jacob S. | 2022-09-11 | 2022-09-15 | 4 | IN PROGRESS
Staffing | Alex B. | 2022-09-16 | 2022-09-17 | 1 | IN PROGRESS
Techincal Reqs. | Frank C. | 2022-09-17 | 2022-09-21 | 4 | NOT STARTED
Testing | Kennedy K. | 2022-09-24 | 2022-10-02 | 8 | NOT STARTED
Dev. Complete | Jacob S. | 2022-10-02 | 2022-10-05 | 3 | NOT STARTED
Hardware Config. | Alex B. | 2022-10-05 | 2022-10-07 | 2 | NOT STARTED
System Testing | Kennedy K. | 2022-10-06 | 2022-10-09 | 3 | NOT STARTED
Launch |  | 2022-10-09 | 2022-10-10 | 1
Percentage of Tasks Complete
Complete | 27.27%
Overdue | 9.091%
In progress | 18.18%
Not Started | 45.45%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4